## Dashboard
GLOMA INTERNATIONAL ¦ TEAM WORK CONTROL CENTER
ClickUp-style overview for Devin & Bishwa • daily updates • pending work • delivered work | [8 empty] | As of | 2026-08-05
TOTAL TASKS |  |  | IN PROGRESS |  | PENDING |  | DELIVERED | OVERDUE | COMPLETION
3 |  |  | 1 |  | 1 |  | 1 | 2 | 33.33%
EMPLOYEE WORKLOAD |  |  |  |  | STATUS MIX
Employee | Total | In Progress | Pending | Delivered | Status | Tasks
Devin | 2 | 1 | 0 | 1 | Pending | 1
Bishwa | 1 | 0 | 1 | 0 | In Progress | 1
[5 empty] | Delivered | 1
[5 empty] | On Hold | 0
HOW THE TEAM SHOULD USE THIS FILE |  |  |  |  | Cancelled | 0
1 Add every assignment to Task Tracker.
2 Update progress, status and Today's Update before leaving work. |  |  |  |  | PRIORITY MIX
3 Add one Daily Updates row for meaningful work completed each day. |  |  |  |  | Priority | Tasks
4 Upload final files to the employee's Drive folder and paste the link. |  |  |  |  | Urgent | 0
5 Copy delivered items to Delivered Work for approval and revision history. |  |  |  |  | High | 2
Tip: Sample rows are included—replace them with live work. |  |  |  |  | Normal | 1
[5 empty] | Low | 0

## Task Tracker
MASTER TASK TRACKER
One row per assignment • use filters to view each employee, client, status or priority
Sample rows 6–8 show the workflow. Replace or delete their input fields when you start using the tracker.
Task ID | Date Assigned | Due Date | Employee | Client / Project | Work Type | Task / Deliverable | Priority | Status | Progress % | Today's Update | Blockers / Notes | Work Folder Link | Final Delivery Link | Last Updated | Days Left | Attention
GLM-260731-001 | 2026-07-31 | 2026-08-01 | Devin | Russel's Dimbula Tea | Video Editing | Edit 15-sec agent recruitment reel | High | In Progress | 65% | Rough cut complete; adding captions and sound mix |  |  |  | 2026-07-31 | -4 | OVERDUE
GLM-260731-002 | 2026-07-31 | 2026-08-03 | Bishwa | Gloma International | Social Media | Prepare August content calendar | Normal | Pending | 15% | Initial topic list drafted | Waiting for campaign confirmation |  |  | 2026-07-31 | -2 | OVERDUE
GLM-260729-003 | 2026-07-29 | 2026-07-30 | Devin | Clean Plus | Video Editing | Final export: 30-sec ASMR car-care reel | High | Delivered | 100% | Final 1080×1920 file exported and delivered |  |  |  | 2026-07-30 |  | DELIVERED
Formulas:
Days Left = IF(OR([Date Assigned]="",[Due Date]="",[Status]="Delivered"),"",[Due Date]-TODAY())
Attention = IF([Date Assigned]="","",IF([Status]="Delivered","DELIVERED",IF(AND([Due Date]<TODAY(),[Status]<>"Delivered"),"OVERDUE",IF([Due Date]-TODAY()<=1,"DUE SOON","ON TRACK"))))

## Daily Updates
DAILY WORK UPDATES
Add one row whenever meaningful progress is made • ideal for end-of-day updates
Use Evidence / Drive Link for previews, working files, screenshots or exported drafts.
Date | Employee | Task ID | Client / Project | Work Completed Today | Hours Spent | Status at End | Next Step | Blockers | Evidence / Drive Link
2026-07-31 | Devin | GLM-260731-001 | Russel's Dimbula Tea | Completed rough cut, captions timing and first sound mix | 3.5 | In Progress | Polish transitions and export review version
2026-07-31 | Bishwa | GLM-260731-002 | Gloma International | Drafted August content themes and arranged the first week | 2 | Pending | Confirm campaign priorities and finalize schedule | Campaign confirmation required

## Delivered Work
DELIVERED WORK REGISTER
Final files, client approval and revision status in one searchable register
Paste the final Google Drive sharing link in Final Drive Link after delivery.
Delivery Date | Employee | Task ID | Client / Project | Deliverable Name | Final Drive Link | Platform / Channel | Client Approval | Revision Status | Notes
2026-07-30 | Devin | GLM-260729-003 | Clean Plus | 30-sec ASMR car-care reel • 1080×1920 |  | Facebook / Instagram | Awaiting | No revision requested | Sample entry—replace with live delivery data.

## Setup & Lists
SETUP, TEAM & DRIVE STRUCTURE
Reference page for owners, workflow rules and the recommended Google Drive folder layout
TEAM ROSTER |  |  |  |  | WORKFLOW RULES
Employee | Primary Role | Update Frequency | Responsibility |  | Every assignment must have one master task row.
Devin | Video Editor • Designer • Social Media Executive | Daily | Update assigned tasks, progress, blockers and all work links |  | Each employee updates status and progress before end of day.
Bishwa | Video Editor • Designer • Social Media Executive | Daily | Update assigned tasks, progress, blockers and all work links |  | Use Daily Updates for the day's meaningful progress.
All finished files go to the employee's Delivered Works folder.
Paste shareable Drive links in the relevant tracker cells.
GOOGLE DRIVE WORKSPACE |  |  |  |  | Mark Delivered only after the final file is uploaded.
Root Folder | Gloma International – Team Work Updates | Devin Delivered Works | https://drive.google.com/open?id=1ntEUrorN4r3IzAU_G-aaSIGOpVbexE8T
Root Folder Link | https://drive.google.com/open?id=1gvnXgvKWVV_SfsrSCIj5jeO1ysO_uI8k | Bishwa Delivered Works | https://drive.google.com/open?id=1VJZjDb4lzJhJ5GPb9ygyZpevEd8fZJ94
Link Access | Gloma team members with access | Shared Briefs & Assets | https://drive.google.com/open?id=1AFi6nTqfGv7b4OKttMdgs-Lwn99nMKN-
RECOMMENDED DRIVE FOLDER STRUCTURE |  |  |  | DROPDOWN VALUES
Level | Folder | Purpose |  | Employees | Statuses | Priorities | Work Types
Root | Gloma International – Team Work Updates | Main shared workspace |  | Devin | Pending | Urgent | Video Editing
01 | 01 Devin | Devin's working area |  | Bishwa | In Progress | High | Graphic Design
01.1 | 01 Devin / Working Files | Editable project files and drafts |  |  | Review | Normal | Social Media
01.2 | 01 Devin / Delivered Works | Final approved or delivered exports |  |  | On Hold | Low | Client Communication
02 | 02 Bishwa | Bishwa's working area |  |  | Delivered |  | Content Planning
02.1 | 02 Bishwa / Working Files | Editable project files and drafts |  |  | Cancelled |  | Ad Campaign
02.2 | 02 Bishwa / Delivered Works | Final approved or delivered exports |  |  |  |  | Other
03 | 03 Shared Briefs & Assets | Client briefs, logos, copy and references
04 | 04 Monthly Archives / 2026 | Closed work organized by month